## Sheet1
Review Comments
Document Name | Doc Version | Comment No | Comment | Comment Date | Reviewer | Related Section | Adjusted by | Status
PMP | V 1.3 | 1 | Please add the review strategy and the change strategy | 25/02/2023 | Amr | Review Strategy | Moataz | Done
PMP | V 1.3 | 2 | Add Link of schedule to appear in a separate section and put it in the reference section at the end. | 25/02/2023 | Amr | schedule management plan | Moataz | Done
PMP | V 1.3 | 3 | Please add specific reviewer form the task | 25/02/2023 | Amr | Version History | Moataz | Done
PMP | V 1.3 | 4 | Please don’t mention names within the document it should be part of the project org charts with the roles and in the rest only mention the role | 25/02/2023 | Amr | Project Management Approach | Moataz | Done
PMP | V 1.3 | 5 | Please add what is in scope and what is out of scope | 25/02/2023 | Amr | Project Scope | Moataz | Done
PMP | V 1.3 | 6 | Milestones not complete please add the deliverables from the project ex: SIQ,SRS,PMP…etc. | 25/02/2023 | Amr | Milestone List | Moataz | Done
PMP | V 1.3 | 7 | Please add detailed steps | 25/02/2023 | Amr | configuration management plan | Moataz | Done
PMP | V 1.3 | 8 | Please remove technical Desgin review and add technical support meetings in General | 25/02/2023 | Amr | communication management plan | Moataz | Done
PMP | V 1.3 | 9 | Please add roles like project manager, Developer | 25/02/2023 | Amr | communication management plan - Roles Table | Moataz | Done
PMP | V 1.3 | 10 | Where is the evidence that this strategy is followed | 25/02/2023 | Amr | Quality management Plan | Moataz | Done
SRS | V 2.0 | 11 | Please don’t add names to the SRS please add it in the document history table with Dates | 25/2/2023 | Amr | Revision History | Hasnaa | Done
SRS | V 2.0 | 12 | Why we have 2 different version 1 also please add description of the changes | 25/2/2023 | Amr | Revision History | Hasnaa | Done
SRS | V 2.0 | 13 | Omar is the customer and he isn’t approving the SRS it should be approved by someone form your team | 25/2/2023 | Amr | Revision History | Hasnaa | Done
SRS | V 2.0 | 14 | Please add real Abbreviations if you have them or if not leave the table empty | 25/2/2023 | Amr | Abbreviations | Hasnaa | Done
SRS | V 2.0 | 15 | Please don’t mention the word module in SRS as it means design please use feature instead | 25/2/2023 | Amr | General Comment | Hasnaa | Done
SRS | V 2.0 | 16 | What you wrote here is fine but it is missing some points: 1) the negative and positive outcomes from each feature should be there. 2) please consolidate all validation conditions related to one feature together. | 25/2/2023 | Amr | System Features | Hasnaa | Done
PMP | V 1.4 | 22 | Remove the version number from the cover page | 2023-10-03 | Amr | Cover Page | Moataz | Done
PMP | V 1.4 | 23 | Readjust the Request status paragragh be divided into (new, In review, Aproved and Implemented) | 2023-10-03 | Amr | Change Strategy | Moataz | Done
PMP | V 1.4 | 24 | Remove the milestone paragraph and keep the table only | 2023-10-03 | Amr | Milesotne List | Moataz | Done
PMP | V 1.4 | 25 | Add the project schedule reference link | 2023-10-03 | Amr | Resource Calender | Moataz | Done
PMP | V 1.4 | 26 | Add naming convention in baseline strategy section | 2023-10-03 | Amr | Baseline Strategy | Moataz | Done
WireFrame | V1.0 | 27 | Share button in wireframe need to be renamed to (add) | 18/3/2023 | Eng. Mohamed Hassan | Add content popup page | Nada | Done
SRS | V3.0 | 28 | Article length should be confirmed in SIQ | 18/3/2023 | Eng. Mohamed Hassan | 3.1.4 Add Feature | Hasnaa | Confirmed
SRS | V3.0 | 29 | Confitrm if Admin can add or delete another admin or not | 18/3/2023 | Eng. Mohamed Hassan | Feature partition | Hasnaa | Confirmed
Class diagram | V1.1 | 30 | what are set category() and getcategory() functions? | 2023-03-20 | Mohamed mazrouaa | Category class | Nada | Justified
Class diagram | V1.1 | 31 | catgory has id or no? | 2023-03-20 | Mohamed mazrouaa | Category class | Nada | Done
Class diagram | V1.1 | 32 | recording class not a photo class. | 2023-03-20 | Mohamed mazrouaa | Recording class | Nada | Done
Class diagram | V1.1 | 33 | the content it self in the (article-video-recording) classes not in content class? | 2023-03-20 | Mohamed mazrouaa | Content class | Nada | Done
Add content Flow chart | V1.1 | 34 | Flowchart should have an start and end | 2023-04-03 | Alaa osama | Add content Flow chart | Moataz | Done
Add content Flow chart | V1.1 | 35 | user should choose from article or upload not ( article/video/record) | 2023-04-03 | Alaa osama | Add content Flow chart | Moataz | Done
Categories Flow chart | V1.1 | 36 | Flowchart should have an start and end | 2023-04-03 | Alaa osama | Categories Flow chart | Moataz | Done
Review comments | V2 | 37 | 18/3 comments need to be added | 2023-04-07 | Mohamed mazrouaa | Review comments document | Moataz | Done
SRS | V 3.0 | 38 | Please Check the "Upload Feature" requirement and its implementation in the wireframe and the front end. The agreed logic to be implemented is that: The user can add video or audio by pressing the "Upload" button and the category of the uploaded file will be identified automatically in the code. | 2023-06-04 | Amr | 3.1.4 Add Feature | Mazrouaa | Done
WireFrame | V1.0 | 39 | Make the signup word in the Login Page in the wireframe a Hyperlink (Blue font and underlined) | 2023-06-04 | Amr | Login Page | alaa | Done
WireFrame | V1.0 | 40 | Please add title of the name of the page like "home Page" In the wireframe and add id to each page to link it in the RTM | 2023-06-04 | Amr | General Comments | alaa | Done
Sequence Diagram | V1.0 | 41 | Check that in the Sequence diagram that i can travel to signup page from the login page | 2023-06-04 | Amr | Login sequence | Mazrouaa | Done
WireFrame | V1.0 | 42 | Check the parameters (username, email. Password, confirm password) of the register page the same in the requirements documents. | 2023-06-04 | Amr | Register Page | Mazrouaa | Done
Website "Front End" | V1.0 | 43 | Remove profile picture from User and Admin Profile page. | 2023-06-04 | Amr | User Profile Page - Admin Profile Page | - | In Progress
SRS | V 3.0 | 44 | In the Admin profile page, we should mention that his email and followed categories will be shown in the page Please add the user profile feature and the Admin profile feature, as the page description what will appear as an information etc. | 2023-06-04 | Amr | System Features | Mazrouaa | Done with another way
ERD | V1.0 | 45 | Remove the unnecessary relations and leave the needed ones only | 2023-06-04 | Amr | General Comment | Mazrouaa | Done
ERD | V1.0 | 46 | Remove the Category entity and add it as an attribute in the content entity | 2023-06-04 | Amr | General Comment | Mazrouaa | Done
ERD | V1.0 | 47 | Remove the Article, Audio and Video entites and add them in one attribute named "Type" in the content entity | 2023-06-04 | Amr | General Comment | Mazrouaa | Done
ERD | V1.0 | 48 | Add "Content Path" attribute in the content entity to know the file path of the uploaded file. | 2023-06-04 | Amr | General Comment | Mazrouaa | Done
Review comments | V 2 | 49 | No evidence for internal reviews | 2023-04-17 | Amr | Review comments document | Moataz | Done
Review comments | V 2 | 50 | Review sheet is too general | 2023-04-17 | Amr | Review comments document | - | Not clear
SRS | V 3 | 51 | SRS-ADD-004 : How to verify that SRS-ADD-007 | 2023-04-17 | Amr | Add feature | Mazrouaa | Done
SRS | V 3 | 52 | SRS-ADD-011 SRS-ADD-012 : no added value | 2023-04-17 | Amr | Add feature | Mazrouaa | done
SRS | V 3 | 53 | SRS-NOTIFI-004 : Will he get notification if any article is added? How will he regiseter? | 2023-04-17 | Amr | Notification feature | Moataz | done
Design document | - | 54 | Design document not found | 2023-04-17 | Amr | Design | hasnaa | done
Sequence diagram | - | 55 | One sequence diagram | 2023-04-17 | Amr | Design | all team members | done
Backend code | - | 56 | Upload and add articles don’t work in categories page | 2023-05-03 | Mazrouaa | Categories page | moataz | done
Design document | V 2 | 57 | Username validation-password validation not in the login diagram construct db function not found | 2023-05-08 | Amr | Design document | hasnaa | Done
sequence daigrams | V 1 | 58 | name of the function delete icon appear | 2023-05-06 | Mazrouaa | get article diagram | nada | done
sequence daigrams | V 1 | 59 | query arrow and its result are in opposite directions database connection not connection | 2023-05-06 | Mazrouaa | get content diagram | Hasnaa | Done
Design document | V 2 | 60 | remove un needed features replace it with components | 2023-05-09 | Mazrouaa | Design document | Mazrouaa | done
Design document | V 3 | 61 | No.comments | 2023-05-11 | Mazrouaa | Design document | - | done
Change request document | V 1 | 62 | The customer change requset need to be added Risk and actions of CR_01 need to be more obvious | 2023-05-12 | Mazrouaa | Change request document | Mazrouaa | Done
Test Report | V 1 | 62 | test cases titels need to be more descriptive | 2023-05-12 | nada | AddUser Feature | Tarek | Done
Test Report | V 1 | 63 | preconditions are confusing in user and admin roles | 2023-05-12 | nada | AddUser Feature | Tarek | Done
Test Report | V 1 | 64 | test steps not clear it seems to be test data not steps | 2023-05-12 | nada | AddUser Feature | Tarek | Done
Test Report | V 1 | 65 | SRS-ADDUSR-001 not covered in testcases | 2023-05-12 | nada | AddUser Feature | Tarek | Done
Test Report | V 1 | 66 | TC_LearningHub_adduser_006 : "too short " is subjective need to be more clear | 2023-05-12 | nada | AddUser Feature | Tarek | Done
Test Report | V 1 | 67 | SRS-ADDUSR-008 not covered in testcases | 2023-05-12 | nada | AddUser Feature | Tarek | Done
Test Report | V 1 | 68 | SRS-ADDUSR-009 not covered in testcases | 2023-05-12 | nada | AddUser Feature | Tarek | Done
Test Report | V 1 | 69 | SRS-ADDUSR-010 not covered in testcases | 2023-05-12 | nada | AddUser Feature | Tarek | Done
| V1 | 70 | Add test case in delete feature to cover " user's can't delete other user's articles | 2023-05-12 | Hasnaa | Delete Feature
Test Report | V 1 | 71 | TC 1 -> User Instead of Normal User (Title) | 2023-05-12 | Alaa | Delete User Feature
Test Report | V 1 | 72 | TC 1 -> User only Instead of normal (ER) | 2023-05-12 | Alaa | Delete User Feature
Test Report | V 1 | 73 | TC 2 -> Admin only Instead of user "Admin" (ER) | 2023-05-12 | Alaa | Delete User Feature
Test Report | V 1 | 74 | Need one test case to validate that User do not have Delete User Button | 2023-05-12 | Alaa | Delete User Feature
Test Report | V 1 | 75 | TC 3,10 - > navigation word in title not clear | 2023-05-12 | Alaa | Navigate Feature
Test Report | V 1 | 76 | TC 4,11 -> How to test redirection to home page if i am already in home page | 2023-05-12 | Alaa | Navigate Feature
Test Report | V 1 | 77 | TC 6,13 -> steps Should include Validate user information | 2023-05-12 | Alaa | Navigate Feature
Test Report | V 1 | 78 | TC 6,13 -> steps Should include Validate user information | 2023-05-12 | Alaa | Navigate Feature
Test Report | V 1 | 79 | TC 4 , TC 5 should be combined | 2023-05-12 | Mazrouaa | Delete User Feature
Test Report | V 1 | 80 | User Credintial used are invalid | 2023-05-12 | Mazrouaa | Delete User Feature
Test Report | V1 | 81 | missing (select category )step in test cases from TC_LearningHub_Add_009 to TC_LearningHub_Add_014 | 2023-05-12 | nada | Add Feature
Test Report | V1 | 82 | testcases title is not descriptive enough | 2023-05-18 | Tarek | Follow Feature
Test Report | V1 | 83 | add this step in the first testcase "1.Find the category page that the user wants to unfollow." | 2023-05-18 | Tarek | Follow Feature
Test Report | V1 | 84 | testcases title is not descriptive enough | 2023-05-18 | Tarek | notification Feature
Test Report | V1 | 85 | the steps of all testcases are not follow the same sequence | 2023-05-18 | Tarek | notification Feature