## Sheet1
PMP - Review Comments
Doc Version | Comment No | Comment | Comment Date | Reviewer | Related Section | Adjusted by
V 1.3 | 1 | Please add the review strategy and the change strategy | 25/02/2023 | Amr | Review Strategy | Moataz
V 1.3 | 2 | Add Link of schedule to appear in a separate section and put it in the reference section at the end. | 25/02/2023 | Amr | schedule management plan | Moataz
V 1.3 | 3 | Please add specific reviewer form the task | 25/02/2023 | Amr | Version History | Moataz
V 1.3 | 4 | Please don’t mention names within the document it should be part of the project org charts with the roles and in the rest only mention the role | 25/02/2023 | Amr | Project Management Approach | Moataz
V 1.3 | 5 | Please add what is in scope and what is out of scope | 25/02/2023 | Amr | Project Scope | Moataz
V 1.3 | 6 | Milestones not complete please add the deliverables from the project ex: SIQ,SRS,PMP…etc. | 25/02/2023 | Amr | Milestone List | Moataz
V 1.3 | 7 | Please add detailed steps | 25/02/2023 | Amr | configuration management plan | Moataz
V 1.3 | 8 | Please remove technical Desgin review and add technical support meetings in General | 25/02/2023 | Amr | communication management plan | Moataz
V 1.3 | 9 | Please add roles like project manager, Developer | 25/02/2023 | Amr | communication management plan - Roles Table | Moataz
V 1.3 | 10 | Where is the evidence that this strategy is followed | 25/02/2023 | Amr | Quality management Plan | Moataz
V 1.4 | 11 | Remove the version number from the cover page | 2023-10-03 | Amr | Cover Page | Moataz
V 1.4 | 12 | Readjust the Request status paragragh be divided into (new, In review, Aproved and Implemented) | 2023-10-03 | Amr | Change Strategy | Moataz
V 1.4 | 13 | Remove the milestone paragraph and keep the table only | 2023-10-03 | Amr | Milesotne List | Moataz
V 1.4 | 14 | Add the project schedule reference link | 2023-10-03 | Amr | Resource Calender | Moataz
V 1.4 | 15 | Add naming convention in baseline strategy section | 2023-10-03 | Amr | Baseline Strategy | Moataz